## Investigation
YTS | 4
Ongoing | 0
Done | 4
Task ID | Work Item |  | POC | Start Date/ Estimate | Comments | Status
| PX4 - Cmake | Build Invocation Flow, Cmake Entry, Make Targets |  |  |  | DONE
|  | Cmake Set up File Investigation, Target Inclusion, Nuttx Inclusion |  |  |  | DONE
|  | Cmake Stub PX4 components - Enable Nuttx Component Inclusion |  |  |  | DONE
| SW Architecture | Investigate Bootloader Boot Up Flows, OS Configuration |  |  |  | DONE
|  | Investigate Application Flow, Task Creation Entry Points |  |  |  | YTS
| Gtest Framework Investigation | Scope out all useable features |  |  |  | YTS
|  | Stream line test report, TC selection and compare with bare metal env |  |  |  | YTS
|  | Investigate Tear down approach at test suite level |  |  |  | YTS

## POC
Task ID | Work Item |  | POC | Start Date/ Estimate | Comments | Status
| Bare Metal Gtest Integration | Cmake Baremetal Env Set up |  |  |  | YTS
|  | Investigate Gtest Integration With Baremetal |  |  |  | YTS
|  | Basic TC with Gtest |  |  |  | YTS
| PX4 Gtest Platform Integration | Validate PX4 Flags with Baremetal gtest build |  |  |  | YTS
|  | Scope out stdlib(printf,scanf) features on px4/nuttx |  |  |  | YTS
|  | Strategize platform entry point and add a entry file |  |  |  | YTS
|  | Compile gtest as lib for px4 target with native flags (std=gnu14) |  |  |  | YTS

## SW BU
YTS | 1
Ongoing | 1
Done | 1
Task ID | Work Item |  | POC | Start Date/ Estimate | Comments | Status
| SW Debug Environment/ Work Flow | Set Up Jlink For Reference Platform With OS Debug Features |  |  |  | DONE
|  | Document Debug Environment Workflow |  |  |  | YTS
| Documentaion | Set up Gihub Doc Repo, Deploy with Jekyll |  |  |  | ONGOING